## Product Backlog
Vision |  | Stock control system that will capture customer orders and update relevant stock items
EPICS/Themes | User story No. | User Stories : As a < type of user >, I want < some goal > so that < some reason > | Priority | Estimates (story points) | Sprint Iteration | Task No | Task Description
Home Page | 1 | As any user of the system I want to view information about the company and a Home screen that will allow me to navigate to customer, supplier, stock or orders screen to carry out my daily work tasks.r and an Exit button | 1 | 1
Customer component | 2 | As any user of the system I need to be able to create a customer record so that I can maintain my customer details. | 1 | 5
| 3 | As any user of the system I need to be able to select a customer record to update so that I can maintain my customer details. | 1 | 1
| 4 | As any user of the system I need to be able to run customer reports so that I can view total sales by industry, area and sales person to monitor our sales. | 1 | 5
| 5 | As any user of the system I need to be able to delete customer records so that I can maintain the system. | 1 | 3
Supplier component | 6 | As any user of the system I need to be able to add suppliers to the system so that we can maintain supplier records | 1 | 3
| 7 | As any user of the system I need to be able to select a supplier record and update it so that I can maintain supplier records | 1 | 1
| 8 | As any user of the systemI need to be able to delete suppliers to the system so that we can maintain supplier records | 1 | 2
Stock component | 9 | As any user of the system I need to be able to add products to the system so that we can maintain product records | 1 | 3
| 10 | As any user of the system I need to be able to update products to the system so that we can maintain product records | 1 | 1
| 11 | As any user of the system I need to be able to delete products to the system so that we can maintain product records | 1 | 2
| 12 | As any user of the system I need to be alerted when stock runs below 5 on any stock item so that I can reorder stock. | 1 | 6
Orders component | 13 | As any user of the system to be able to order multiple products for a customer order so that I can place orders for customers of items that are currently in stock. | 1 | 6
| 14 | As any user of the system I need to be view the total cost of a customer order so that I can see money due. | 1 | 3
| 15 | As any user of the system I can update the status of an order to maintain the order tracking. | 1 | 2
|  | Total Points |  | 44
|  | Team Capacity |  | 20

## Sprint 1 Backlog
User Story No. | Story Points | Task No. | Status | Hours remaining | Actual Time taken | Tasks | Person
Home Page | 1 | As any user of the system I want to view information about the company and a Home screen that will allow me to navigate to customer, supplier, stock or orders screen to carry out my daily work tasks.r and an Exit button | 1 | 1 |  | make menu and home
Customer component | 2 | As any user of the system I need to be able to create a customer record so that I can maintain my customer details. | 1 | 5 |  | create customer class (add - county+ country)
| 3 | As any user of the system I need to be able to select a customer record to update so that I can maintain my customer details. | 1 | 1 |  | access list from menu
| 4 | As any user of the system I need to be able to run customer reports so that I can view total sales by industry, area and sales person to monitor our sales. | 1 | 5 |  | get input for type, find type and sum
| 5 | As any user of the system I need to be able to delete customer records so that I can maintain the system. | 1 | 3 |  | loop and delete
Supplier component | 6 | As any user of the system I need to be able to add suppliers to the system so that we can maintain supplier records | 1 | 3 |  | create supplier class

## Sprint 2 Backlog
User Story No. | Story Points | Task No. | Status | Hours remaining | Actual Time taken | Task
| 7 | As any user of the system I need to be able to select a supplier record and update it so that I can maintain supplier records | 1 | 1
| 8 | As any user of the systemI need to be able to delete suppliers to the system so that we can maintain supplier records | 1 | 2
Stock component | 9 | As any user of the system I need to be able to add products to the system so that we can maintain product records | 1 | 3
| 10 | As any user of the system I need to be able to update products to the system so that we can maintain product records | 1 | 1
| 11 | As any user of the system I need to be able to delete products to the system so that we can maintain product records | 1 | 2
| 12 | As any user of the system I need to be alerted when stock runs below 5 on any stock item so that I can reorder stock. | 1 | 6

## Sprint 3 Backlog
Orders component | 13 | As any user of the system to be able to order multiple products for a customer order so that I can place orders for customers of items that are currently in stock. | 1 | 6
| 14 | As any user of the system I need to be view the total cost of a customer order so that I can see money due. | 1 | 3
| 15 | As any user of the system I can update the status of an order to maintain the order tracking. | 1 | 2